## Task_Table
ID | Active | Task Mode | Name | Duration | Start | Finish | Predecessors | Outline Level | Notes
1 | Yes | Manually Scheduled | Project Setup | 29 days | January 2, 2018 8:00 AM | February 9, 2018 5:00 PM |  | 1
2 | Yes | Auto Scheduled | Gain Access to FLL Server | 1 day | December 11, 2017 8:00 AM | December 11, 2017 5:00 PM |  | 2
3 | Yes | Auto Scheduled | Order DreamWeaver | 1 day | December 12, 2017 8:00 AM | December 12, 2017 5:00 PM |  | 2
4 | Yes | Auto Scheduled | Define Project scope with Eric/Gayann | 5 days | December 11, 2017 8:00 AM | December 15, 2017 5:00 PM |  | 2
5 | Yes | Auto Scheduled | Develop Project Plan/Timeline with deliverable schedule | 2 days | January 15, 2018 8:00 AM | January 16, 2018 5:00 PM |  | 2
6 | Yes | Auto Scheduled | Talk to leading developer on project background | 3 days | December 18, 2017 8:00 AM | December 20, 2017 5:00 PM |  | 2
7 | Yes | Auto Scheduled | Familiarize/locate all data files needed - what's missing? | 5 days | December 18, 2017 8:00 AM | December 22, 2017 5:00 PM |  | 2
8 | Yes | Auto Scheduled | Scrub Excel FLL content/categories/URLS | 7 days | January 2, 2018 8:00 AM | January 10, 2018 5:00 PM |  | 2
9 | Yes | Manually Scheduled | Create Operating rhythm weekly tag ups |  | January 12, 2018 8:00 AM |  |  | 2
10 | Yes | Auto Scheduled | Send reoccuring weekly tag in to Eric/Gayann | 1 day | January 17, 2018 8:00 AM | January 17, 2018 5:00 PM |  | 3
11 | Yes | Auto Scheduled | Source 'Manager' Pilot user group | 4 days | January 16, 2018 8:00 AM | January 19, 2018 5:00 PM |  | 2
12 | Yes | Auto Scheduled | Design | 9 days | January 8, 2018 8:00 AM | January 18, 2018 5:00 PM |  | 1
13 | Yes | Auto Scheduled | Define/Consolidate Homepage categories | 2 days | January 8, 2018 8:00 AM | January 9, 2018 5:00 PM |  | 2
14 | Yes | Auto Scheduled | Eric Front Page Buyoff | 0 days | January 18, 2018 8:00 AM | January 18, 2018 8:00 AM |  | 2
15 | Yes | Auto Scheduled | Incorporate Eric Feedback | 1 day | January 18, 2018 8:00 AM | January 18, 2018 5:00 PM | 14 | 2
16 | Yes | Auto Scheduled | Validate Level-2 page links (all working?) | 1 day | January 18, 2018 8:00 AM | January 18, 2018 5:00 PM |  | 2
17 | Yes | Auto Scheduled | Validate Content | 1 day | January 18, 2018 8:00 AM | January 18, 2018 5:00 PM |  | 3
18 | Yes | Auto Scheduled | Validate URL's | 1 day | January 18, 2018 8:00 AM | January 18, 2018 5:00 PM |  | 3
19 | Yes | Auto Scheduled | Create Level-2 Design | 1 day | January 17, 2018 8:00 AM | January 17, 2018 5:00 PM |  | 2
20 | Yes | Auto Scheduled | Duplicate prototype CSS design on 'second-click' template | 1 day | January 18, 2018 8:00 AM | January 18, 2018 5:00 PM | 19 | 2
21 | Yes | Manually Scheduled | Development |  |  |  |  | 1
22 | Yes | Auto Scheduled | SEO - Total Access w/ IT | 5 days | January 22, 2018 8:00 AM | January 26, 2018 5:00 PM |  | 2
23 | Yes | Auto Scheduled | Intranet Site-search integration in FLL website | 5 days | January 24, 2018 8:00 AM | January 30, 2018 5:00 PM | 24 | 2
24 | Yes | Manually Scheduled | Level-1 Dev | 5 days | January 17, 2018 8:00 AM | January 23, 2018 5:00 PM |  | 2
25 | Yes | Auto Scheduled | Source logos for buttons | 1 day | January 17, 2018 8:00 AM | January 17, 2018 5:00 PM |  | 3
26 | Yes | Auto Scheduled | Add logos to buttons | 1 day | January 17, 2018 8:00 AM | January 17, 2018 5:00 PM |  | 3
27 | Yes | Auto Scheduled | Align font sizes on Buttons | 1 day | January 17, 2018 8:00 AM | January 17, 2018 5:00 PM |  | 3
28 | Yes | Auto Scheduled | Leadership Compass - increase text size on image | 1 day | January 17, 2018 8:00 AM | January 17, 2018 5:00 PM |  | 3
29 | Yes | Auto Scheduled | Create summary text for each button | 1 day | January 17, 2018 8:00 AM | January 17, 2018 5:00 PM |  | 3
30 | Yes | Auto Scheduled | Remove additional Drop-down menus | 1 day | January 17, 2018 8:00 AM | January 17, 2018 5:00 PM |  | 3
31 | Yes | Auto Scheduled | Add Level-2 Drop-down menu bar items | 1 day | January 17, 2018 8:00 AM | January 17, 2018 5:00 PM |  | 3
32 | Yes | Auto Scheduled | Update Home-page META tags / Title | 1 day | January 17, 2018 8:00 AM | January 17, 2018 5:00 PM |  | 3
33 | Yes | Auto Scheduled | Mobile: create mobile design | 1 day? | January 17, 2018 8:00 AM | January 17, 2018 5:00 PM |  | 3
34 | Yes | Manually Scheduled | Level-2 Dev | 1 day? | January 18, 2018 8:00 AM | January 18, 2018 5:00 PM |  | 2
35 | Yes | Auto Scheduled | Boeing Production Systems | 1 day | January 18, 2018 8:00 AM | January 18, 2018 5:00 PM |  | 3
36 | Yes | Auto Scheduled | Develop Yourself & Team | 1 day | January 19, 2018 8:00 AM | January 19, 2018 5:00 PM | 35 | 3
37 | Yes | Auto Scheduled | FOD | 1 day | January 22, 2018 8:00 AM | January 22, 2018 5:00 PM | 36 | 3
38 | Yes | Auto Scheduled | Saftey | 1 day | January 23, 2018 8:00 AM | January 23, 2018 5:00 PM | 37 | 3
39 | Yes | Auto Scheduled | Drawings Specs & Procedures | 1 day | January 19, 2018 8:00 AM | January 19, 2018 5:00 PM |  | 3
40 | Yes | Auto Scheduled | Manage Team & Performance | 1 day | January 19, 2018 8:00 AM | January 19, 2018 5:00 PM |  | 3
41 | Yes | Auto Scheduled | Project Management & Processes | 1 day | January 19, 2018 8:00 AM | January 19, 2018 5:00 PM |  | 3
42 | Yes | Auto Scheduled | Tool Management Control & Accountability | 1 day | January 19, 2018 8:00 AM | January 19, 2018 5:00 PM |  | 3
43 | Yes | Auto Scheduled | Mobile: Create mobile design | 1 day? | January 18, 2018 8:00 AM | January 18, 2018 5:00 PM |  | 3
44 | Yes | Auto Scheduled | Pilot / Validation | 10 days? | January 29, 2018 8:00 AM | February 9, 2018 5:00 PM |  | 2
45 | Yes | Auto Scheduled | Pilot User-Group Test (A) | 3 days? | January 29, 2018 8:00 AM | January 31, 2018 5:00 PM |  | 3
46 | Yes | Auto Scheduled | Incorporate Feedback | 1 day? | January 31, 2018 8:00 AM | January 31, 2018 5:00 PM |  | 3
47 | Yes | Auto Scheduled | Pilot User-Group Test (B) | 5 days? | February 1, 2018 8:00 AM | February 7, 2018 5:00 PM |  | 3
48 | Yes | Auto Scheduled | Incorporate Feedback | 3 days? | February 7, 2018 8:00 AM | February 9, 2018 5:00 PM |  | 3
49 | Yes | Auto Scheduled | Go-Live | 1 day? | February 9, 2018 8:00 AM | February 9, 2018 5:00 PM |  | 1
50 | Yes | Auto Scheduled | Upload new FFL site to 'staging' | 1 day? | February 9, 2018 8:00 AM | February 9, 2018 5:00 PM |  | 2
51 | Yes | Auto Scheduled | Upload to Live-site / CUT-OVER | 1 day? | February 9, 2018 8:00 AM | February 9, 2018 5:00 PM |  | 2
52 | Yes | Auto Scheduled | Post- Live Website | 10 days? | February 12, 2018 8:00 AM | February 23, 2018 5:00 PM |  | 1
53 | Yes | Auto Scheduled | Create OneNote Maintenance document | 5 days? | February 12, 2018 8:00 AM | February 16, 2018 5:00 PM |  | 2
54 | Yes | Auto Scheduled | Create Regulatory audit calendar | 1 day? | February 19, 2018 8:00 AM | February 19, 2018 5:00 PM |  | 2
55 | Yes | Auto Scheduled | Validate Future web-site administration logistics | 1 day? | February 22, 2018 8:00 AM | February 22, 2018 5:00 PM |  | 2 | Per Gayann, I will be responsible for website maintenance. I am proposing regulatory audit checks and website feedback though customer useage. 1/12/18
56 | Yes | Auto Scheduled | Tip Sheet for Editing | 4 days? | February 20, 2018 8:00 AM | February 23, 2018 5:00 PM |  | 2
57 | Yes | Auto Scheduled | Mobile | 3 days? | February 21, 2018 8:00 AM | February 23, 2018 5:00 PM |  | 2
58 | Yes | Auto Scheduled | Tip Sheet for accessability through mobile devices | 3 days? | February 21, 2018 8:00 AM | February 23, 2018 5:00 PM |  | 3

## Resource_Table
ID | Name | Initials | Type | Material Label | Group | Email Address | User Logon Account | Max Units | Standard Rate | Cost Per Use | Notes

## Assignment_Table
Task Name | Resource Name | % Work Complete | Work | Units